# Population Health Leadership Quarterly Review Facilitator’s Guide

# Meeting Guidance

Length: Recommended 60-minute meeting in person, if feasible

Participants: Population Health Leadership Team (PHLT) and members of the Implementation Teams, as needed

Quarterly Cadence: June, September, December 2026

Facilitator: PHMI Lead, or agreed upon facilitator

Optional: PT Coach (this is up to the discretion of the PHLT)

Purpose: The goal of the quarterly reviews is to advance the three SMARTIE goals. This suggested format allows the PHLT to monitor progress of PHM goals over 2026.

# Meeting Preparation

- See Quarterly Review Meeting Guidance for suggested pre-meeting, during meeting, and post-meeting activities.

- Meet your Center’s PT Coach to prepare for the meeting at least two weeks prior to the meeting.

- A suggested participant agenda and slide template is provided based on the prompts in this Facilitator’s Guide.

- The PT Coach is not required to attend provided they are informed of changes to goals, strategies, or implementation plan.

- If you don’t have time to discuss certain content during the meeting, consider creating an appendix that includes other important data or context.

# Meeting Objectives

- Review progress toward SMARTIE Goals

- Review what is needed to support our PHM Culture and Goals

- Review what changes to our plan need to be made based on this review

# High Level Agenda

- Welcome/Setting the Stage (7 minutes)

- 2026 SMARTIE Goals and Progress this Quarter (35 minutes)

- Supporting PHM Culture and Capacity (8–10 minutes)

- Action Items/Next Steps (3–5 minutes)

Facilitator Detailed Agenda Table (See suggested prompts listed below the agenda table to tailor discussion for each topic)

| Topic/Time | Facilitator Prompts | Slides, Reference Doc |
| --- | --- | --- |
| Welcome/ Settling In 5 minutes | Assumes the facilitator starts the meeting 2 minutes after the scheduled start time. Title Slide and Agenda Welcome, Overview of Agenda, Introduce Parking Lot: “There will likely be topics that surface that are outside of what we can cover today. We will capture them in a ‘parking lot’ to determine next steps after the meeting.” Our PHM Vision Statement - “Our North Star” | Title and agenda slide Slide: (Parking Lot placeholder) Slide: Vision Statement |
| Clinical Outcome Goal 10-15m | - Review goal statement, champion/leads/structure, change strategies, key activities - Review PDSAs, key implementation activities this quarter - Review run charts for measures associated with goal* - Add 1-3 discussion points (**See prompts below) | Slide: goal statement, champion/leads/structure Slide: Progress on key activities Slide: Consolidated and annotated run charts for 1 or more measures. |
| Sustainability Goal 10-15m | - Review goal statement - Outline champion/team, key activities this quarter - Review run charts associated with measures for this goal - Add 1-3 discussion prompts** | Slide with goal statement, champion/leads/structure Slide with key activities and progress this quarter Slide with consolidated and annotated run charts |
| Spread Goal 10-15m | Note: depending on the timing of center Spread goal, this may be tabled beyond goal statement in June review. - Review Goal Statement - Outline, champion/team, and the Spread plan (strategy selected, to where, by when) - Outline progress towards implementation - Review run charts associated with measures for this goal and other key metrics - Review PDSAs, if conducted in this quarter, as it relates to testing strategy in new location/program - Add 1-3 discussion prompts** | Slide with goal statement, champion, leads, structure Slide with key activities and progress this quarter Slide with consolidated and annotated run charts (all measures on one slide if feasible) |
| Supporting PHM Culture and Capacity 10 minutes | Suggested prompts to be tailored to your Center: - What course corrections (if any) do we need in our implementation plan? What do we need from you (leaders) to support improvement/changes and move us to goal? - Where are we seeing progress in building a PHM culture? - How are we aligning PHM to organizational priorities? - What needs to be communicated, to whom, by when? | Slide with prompts |
| Actions/Next Steps 4 minutes | - Next steps and actions recapped by Facilitator - Parking lot: where do these questions get addressed? - Acknowledgements and adjourn | Slide for next steps |

# ** Discussion Prompts

These are illustrative prompts that could be selected in the goal sections

## Discussion Prompts: Progress this Quarter (PDSA, Key Activities, and Data Review [Run Charts])

- Do these selected change strategies appear to be effective (moving us towards goal)? If not, is there a lag time before we see change?

- What did we expect to see?

- In what ways do we need to reinforce ‘uptake’ of the change strategy and/or key activities? (Training, communications, other?)

- Are there any HIT/tech issues that need to be addressed?

- Do we need to change course, and if so, to what? (Review other change strategies, change in roles, infrastructure, more training, etc.)

## Discussion Prompts: Data Collection and Reporting (Building our Improvement Data Capacity)

- We have had challenges collecting data. Formulate an ‘ask’ for leaders on what support is needed in collecting data for one or more process or balancing measure.

- What is the story behind the numbers (specific to a run chart or across a series of run charts associated with a goal)?

  - Ask leaders to interpret the run chart: do they believe strategies are leading to improvement?

  - Do we need to rethink our theory of what will lead to improvement?

- Discuss what a trend is (three or more data cycles). Educate leaders on how we use trends in improvement data referencing one or more charts.

- If data is stratified by provider/teams, what variation are you seeing? What does this indicate in terms of potential resistance? What actions are needed, specifically from leaders?

- Are we leveraging our PHM platform to collect data? If not, what are the barriers and what do we need from leaders?

- What additional data might we need and why?

- Do we need to consider patient feedback?

## Discussion Prompts: Culture/Change Management

- Are there changes in the environment that we need to consider that inform our goals and quarterly plans?

- What successes have we seen over this last quarter in building a PHM culture?

- How can we reinforce these wins? In what meetings and other communication venues?

- Who needs to be acknowledged publicly (and in what settings)?

- What organizational barriers may disrupt progress? How can we mitigate this?

- What are other considerations to move us towards goal?